## Frontpage
New Hire Onboarding Toolkit
Dann Bleeker Pedersen
StruktureretSundFornuft.dk
How to use this template
1. Start in MasterData — enter the new hire's name, manager, and key dates (offer date, start date). Every other sheet pulls from these cells.
2. Onboarding checklist — the master task list from offer to trial-period evaluation. Deadlines and status update automatically; mark a task "Yes" in the Completed column once it's done.
3. Onboarding program — the new hire's schedule for the first weeks. Add or edit meetings as they get arranged.
4. Pre-read package — materials to send before day one. Mark items "Yes" in Completed as you send them.
5. High level status — a live dashboard summarizing progress by phase and listing everything currently overdue.
Tip: the dashboard uses PivotTables — after editing the checklist, click Data ▸ Refresh All (or right-click the dashboard ▸ Refresh) to pull in the latest status.
Reusing this for the next hire
1. In MasterData, update the new hire's name, manager, HR contact, IT contact, buddy, and Start-date — dates and the dashboard recalculate automatically.
2. In Onboarding checklist and Pre-read package, reset every "Completed" cell back to "No" (or blank) so nothing carries over from the last hire.
3. Review the Owner Role column in the checklist — it defaults to Manager/HR/IT/Buddy per task, but adjust any row that works differently on your team.

## High level status
Tip: after updating the Onboarding checklist, click Data ▸ Refresh All so the numbers and lists below stay current.
Overview of progress per phase
|  | Count of Activity | Column Labels
|  | Row Labels | On track | Overdue
|  | Acceptance | 0% | 100%
|  | Finished onboarding | 100% | 0%
|  | Introduction period | 100% | 0%
|  | Make final agreement | 0% | 100%
|  | Preparation for start of new hire | 37.68% | 62.32%
|  | Grand Total | 53.73% | 46.27%
|  | Status (automatic) | Overdue
Overdue tasks
Row Labels
Acceptance
Agree on start date with new hire
Create position in HR system
Inform HR about acceptance
Inform your manager about acceptance
Mark recruitment as completed in list of open recruitments
Send official contract with start-date
Receive acceptance
Get signed contract returned (electronic signature is fine)
Confirm with HR that they have received all needed paperwork
Verify ID and right-to-work documentation
Get signed NDA/confidentiality agreement returned
Send welcome email to new hire (see Welcome Email sheet)
Make final agreement
Ask if new hire needs any other information to make decision
| Enroll in ​Leadership Programme, if relevant | Contact (written or orally) new hire and ask if they have any follow-up questions. Remind of deadline
Create and validate written offer of employment
Inform new hire about deadline for making final decision
Make offer (oral)
Send written offer of employment with all terms and conditions
Verify job description
| Order personnel card and other ID | Preparation for start of new hire
Ask for bank account number to setup salary payment
Ask team to schedule personal introductory 1:1 meetings during the first month. Ask for feedback when scheduled.
Assign first day contact person, if manager is not able to attend
Block time to be with new hire on the first day, and during first week
Brief team on onboarding process, and ask for changes
Call new hire with update on the stakeholder list produced, and ask for any requests
Contact new hire and agree on which computer, phone and software and hardware accessories to order
Create first day plan
Enroll in relevant other trainings (systems, etc.)
Find desk / placement
Identify all current meetings that new hire should attend, and add to onboarding program
Identify key stakeholders for information about new hire
Inform key stakeholders of new hire and start-date
Inform team of new hire and start-date
Order business cards, if needed
Order hardware and software
Order phone and phonenumber
Order welcome package
Plan for tour of relevant company buildings/areas and update onboarding program
Schedule 1:1 meetings with manager. Weekly in trial period
Schedule hand-over meeting with old manager, if relevant
Schedule intro meetings with identified stakeholders, and update onboarding program
Schedule introduction to financial management and current numbers
Schedule introduction to meeting structure
Schedule introduction with HR Partner and C&B specialist
Schedule team for lunch on first day
Send first day plan to new hire - CC team
Update onboarding program with scheduled introductions
Contact new hire and agree on check-in conversations from now, until start. Minimum frequency every 2 weeks
Update onboarding program with enrolled trainings and introductions
Order any special software
Connect on LinkedIn, if appropriate
Identify offices, conference rooms, etc. where special access is required. Request access
Schedule breakfast and lunch with team on the first day
Order breakfast for first day
Invite team to breakfast on first day
Publish information about new hire on department site,newsletter, etc. (including start-date)
Create empty template onboarding program (see seperate sheet)
Enrollment in IT onboarding
Enrollment in "new manager in company" onboarding
Enroll in ​Leadership Programme, if relevant
Order personnel card and other ID
Schedule go and see with any relevant stakeholders.
Grand Total
Schedule go and see with any relevant stakeholders.
Tour of building
Instruct in use of HR systems + get contacts setup with birthdates
Introduction to HR contact persons

## MasterData
New Hire Onboarding — Key Dates
Name of new hire | [New Hire Name]
Date of giving offer of employment | 2026-06-12
Deadline for accepting offer | 2026-06-20
Date of offer acceptance | 2026-06-20
Start-date | 2026-08-02
Buddy | [Buddy Name]
Manager | [Manager Name]
HR Contact | [HR Contact Name]
IT Contact | [IT Contact Name]
StruktureretSundFornuft.dk
Enroll in ​Leadership Programme, if relevant
Order personnel card and other ID
Schedule go and see with any relevant stakeholders.
Tour of building
Instruct in use of HR systems + get contacts setup with birthdates
Introduction to HR contact persons

## Onboarding checklist
Phase | Activity | DaysOffset | Offsetting date | Responsible | Deadline | Status (automatic) | Completed | Remarks | Owner Role
Make final agreement |  |  |  |  | 2026-06-17 | Overdue
Make final agreement | Make offer (oral) | 0 | 2026-06-12 | [Manager Name] | 2026-06-12 | Overdue |  |  | Manager
Make final agreement | Verify job description | 0 | 2026-06-12 | [Manager Name] | 2026-06-12 | Overdue |  |  | Manager
Make final agreement | Create and validate written offer of employment | 0 | 2026-06-12 | [Manager Name] | 2026-06-12 | Overdue |  |  | Manager
Make final agreement | Send written offer of employment with all terms and conditions | 1 | 2026-06-12 | [Manager Name] | 2026-06-15 | Overdue |  |  | Manager
Make final agreement | Ask if new hire needs any other information to make decision | 1 | 2026-06-12 | [Manager Name] | 2026-06-15 | Overdue |  |  | Manager
Make final agreement | Inform new hire about deadline for making final decision | 1 | 2026-06-12 | [Manager Name] | 2026-06-15 | Overdue |  |  | Manager
Make final agreement | Contact (written or orally) new hire and ask if they have any follow-up questions. Remind of deadline | 3 | 2026-06-12 | [Manager Name] | 2026-06-17 | Overdue |  |  | Manager
Acceptance |  |  |  |  | 2026-06-25 | Overdue
Acceptance | Receive acceptance | 0 | 2026-06-20 | [Manager Name] | 2026-06-20 | Overdue |  |  | Manager
Acceptance | Verify ID and right-to-work documentation | 1 | 2026-06-20 | [HR Contact Name] | 2026-06-22 | Overdue |  |  | HR
Acceptance | Agree on start date with new hire | 0 | 2026-06-20 | [Manager Name] | 2026-06-20 | Overdue |  |  | Manager
Acceptance | Inform HR about acceptance | 0 | 2026-06-20 | [Manager Name] | 2026-06-20 | Overdue |  |  | Manager
Acceptance | Create position in HR system | 0 | 2026-06-20 | [HR Contact Name] | 2026-06-20 | Overdue |  |  | HR
Acceptance | Send official contract with start-date | 1 | 2026-06-20 | [HR Contact Name] | 2026-06-22 | Overdue |  |  | HR
Acceptance | Get signed contract returned (electronic signature is fine) | 4 | 2026-06-20 | [HR Contact Name] | 2026-06-25 | Overdue |  |  | HR
Acceptance | Get signed NDA/confidentiality agreement returned | 4 | 2026-06-20 | [HR Contact Name] | 2026-06-25 | Overdue |  |  | HR
Acceptance | Mark recruitment as completed in list of open recruitments | 4 | 2026-06-20 | [HR Contact Name] | 2026-06-25 | Overdue |  |  | HR
Acceptance | Inform your manager about acceptance | 4 | 2026-06-20 | [Manager Name] | 2026-06-25 | Overdue |  |  | Manager
Acceptance | Confirm with HR that they have received all needed paperwork | 4 | 2026-06-20 | [Manager Name] | 2026-06-25 | Overdue |  |  | Manager
Acceptance | Send welcome email to new hire (see Welcome Email sheet) | 2 | 2026-06-20 | [Manager Name] | 2026-06-23 | Overdue |  |  | Manager
Preparation for start of new hire |  |  |  |  | 2026-08-02 | Overdue
Preparation for start of new hire | Inform team of new hire and start-date | 1 | 2026-06-20 | [Manager Name] | 2026-06-22 | Overdue |  |  | Manager
Preparation for start of new hire | Identify key stakeholders for information about new hire | 0 | 2026-06-20 | [Manager Name] | 2026-06-20 | Overdue |  |  | Manager
Preparation for start of new hire | Inform key stakeholders of new hire and start-date | 1 | 2026-06-20 | [Manager Name] | 2026-06-22 | Overdue |  |  | Manager
Preparation for start of new hire | Publish information about new hire on department site,newsletter, etc. (including start-date) | 2 | 2026-06-20 | [Manager Name] | 2026-06-23 | Overdue |  |  | Manager
Preparation for start of new hire | Create onboarding pre-read package by adapting template (see separate sheet) | -10 | 2026-08-02 | [Manager Name] | 2026-07-20 | On track |  |  | Manager
Preparation for start of new hire | Send onboarding pre-read package | -5 | 2026-08-02 | [Manager Name] | 2026-07-27 | On track |  |  | Manager
Preparation for start of new hire | Contact new hire and agree on check-in conversations from now, until start. Minimum frequency every 2 weeks | 3 | 2026-06-20 | [Manager Name] | 2026-06-24 | Overdue |  |  | Manager
Preparation for start of new hire | Create empty template onboarding program (see seperate sheet) | 0 | 2026-06-20 | [Manager Name] | 2026-06-20 | Overdue |  |  | Manager
Preparation for start of new hire | Enrollment in onboarding | 0 | 2026-06-20 | [Manager Name] | 2026-06-20 | Overdue |  |  | Manager
Preparation for start of new hire | Enrollment in "new manager in company" onboarding | 0 | 2026-06-20 | [Manager Name] | 2026-06-20 | Overdue |  |  | Manager
Preparation for start of new hire | Enroll in ​Leadership Programme, if relevant | 0 | 2026-06-20 | [Manager Name] | 2026-06-20 | Overdue |  |  | Manager
Preparation for start of new hire | Enroll in relevant other trainings (systems, etc.) | 0 | 2026-06-20 | [Manager Name] | 2026-06-20 | Overdue |  |  | Manager
Preparation for start of new hire | Update onboarding program with enrolled trainings and introductions | 0 | 2026-06-20 | [Manager Name] | 2026-06-20 | Overdue |  |  | Manager
Preparation for start of new hire | Contact new hire and agree on which computer, phone and software and hardware accessories to order | 3 | 2026-06-20 | [Manager Name] | 2026-06-24 | Overdue |  |  | Manager
Preparation for start of new hire | Order hardware and software | 3 | 2026-06-20 | [IT Contact Name] | 2026-06-24 | Overdue |  |  | IT
Preparation for start of new hire | Order any special software | 3 | 2026-06-20 | [IT Contact Name] | 2026-06-24 | Overdue |  |  | IT
Preparation for start of new hire | Order personnel card and other ID | 3 | 2026-06-20 | [IT Contact Name] | 2026-06-24 | Overdue |  |  | IT
Preparation for start of new hire | Order welcome package | 3 | 2026-06-20 | [Manager Name] | 2026-06-24 | Overdue |  |  | Manager
Preparation for start of new hire | Find desk / placement | 3 | 2026-06-20 | [Manager Name] | 2026-06-24 | Overdue |  |  | Manager
Preparation for start of new hire | Appoint buddy | -7 | 2026-08-02 | [Manager Name] | 2026-07-23 | On track |  |  | Manager
Preparation for start of new hire | Inform new-hire about buddy | -7 | 2026-08-02 | [Manager Name] | 2026-07-23 | On track |  |  | Manager
Preparation for start of new hire | Walk through buddy responsibilities with buddy | -3 | 2026-08-02 | [Manager Name] | 2026-07-29 | On track |  |  | Manager
Preparation for start of new hire | Ask buddy to contact new hire and introduce themselves | -3 | 2026-08-02 | [Buddy Name] | 2026-07-29 | On track |  |  | Buddy
Preparation for start of new hire | Schedule buddy meeting for first-day and update onboarding program | -3 | 2026-08-02 | [Manager Name] | 2026-07-29 | On track |  |  | Manager
Preparation for start of new hire | Review current planned meetings and incorporate them in onboarding program | -2 | 2026-08-02 | [Manager Name] | 2026-07-30 | On track |  |  | Manager
Preparation for start of new hire | Make a list of people, that the new hire should be introduced to in the onboarding program | -1 | 2026-08-02 | [Manager Name] | 2026-07-31 | On track |  |  | Manager
Preparation for start of new hire | Call new hire with update on the stakeholder list produced, and ask for any requests | 2 | 2026-06-20 | [Manager Name] | 2026-06-23 | Overdue |  |  | Manager
Preparation for start of new hire | Schedule intro meetings with identified stakeholders, and update onboarding program | 3 | 2026-06-20 | [Manager Name] | 2026-06-24 | Overdue |  |  | Manager
Preparation for start of new hire | Ensure access to sharepoint sites, teams, etc. | 0 | 2026-08-02 | [IT Contact Name] | 2026-08-02 | On track |  |  | IT
Preparation for start of new hire | Create IT account and company email for new hire | -3 | 2026-08-02 | [IT Contact Name] | 2026-07-29 | On track |  |  | IT
Preparation for start of new hire | Ask team to schedule personal introductory 1:1 meetings during the first month. Ask for feedback when scheduled. | 4 | 2026-06-20 | [Manager Name] | 2026-06-25 | Overdue |  |  | Manager
Preparation for start of new hire | All team members have confirmed introduction meetings | -1 | 46236 | [Manager Name] | 2026-07-31 | On track |  |  | Manager
Preparation for start of new hire | Brief team on onboarding process, and ask for changes | 4 | 2026-06-20 | [Manager Name] | 2026-06-25 | Overdue |  |  | Manager
Preparation for start of new hire | Connect on LinkedIn, if appropriate | 0 | 2026-06-20 | [Manager Name] | 2026-06-20 | Overdue |  |  | Manager
Preparation for start of new hire | Identify offices, conference rooms, etc. where special access is required. Request access | 0 | 2026-06-20 | [Manager Name] | 2026-06-20 | Overdue |  |  | Manager
Preparation for start of new hire | Order phone and phonenumber | 3 | 2026-06-20 | [IT Contact Name] | 2026-06-24 | Overdue |  |  | IT
Preparation for start of new hire | Order business cards, if needed | 3 | 2026-06-20 | [Manager Name] | 2026-06-24 | Overdue |  |  | Manager
Preparation for start of new hire | Assign first day contact person, if manager is not able to attend | 4 | 2026-06-20 | [Manager Name] | 2026-06-25 | Overdue |  |  | Manager
Preparation for start of new hire | Create first day plan | 4 | 2026-06-20 | [Manager Name] | 2026-06-25 | Overdue |  |  | Manager
Preparation for start of new hire | Send first day plan to new hire - CC team | 5 | 2026-06-20 | [Manager Name] | 2026-06-26 | Overdue |  |  | Manager
Preparation for start of new hire | Order office equipment (table, etc.), if needed | -10 | 2026-08-02 | [Manager Name] | 2026-07-20 | On track |  |  | Manager
Preparation for start of new hire | Ask for bank account number to setup salary payment | 0 | 2026-06-20 | [HR Contact Name] | 2026-06-20 | Overdue |  |  | HR
Preparation for start of new hire | Schedule breakfast and lunch with team on the first day | 4 | 2026-06-20 | [Manager Name] | 2026-06-25 | Overdue |  |  | Manager
Preparation for start of new hire | Order breakfast for first day | 4 | 2026-06-20 | [Manager Name] | 2026-06-25 | Overdue |  |  | Manager
Preparation for start of new hire | Send welcome letter to home address | -10 | 2026-08-02 | [Manager Name] | 2026-07-20 | On track |  |  | Manager
Preparation for start of new hire | Collect emergency contact details from new hire | -9 | 2026-08-02 | [Manager Name] | 2026-07-21 | On track |  |  | Manager
Preparation for start of new hire | Block time to be with new hire on the first day, and during first week | 0 | 2026-06-20 | [Manager Name] | 2026-06-20 | Overdue |  |  | Manager
Preparation for start of new hire | Determine performance goals for new hire during first 12 months | -10 | 2026-08-02 | [Manager Name] | 2026-07-20 | On track |  |  | Manager
Preparation for start of new hire | Identify assignments that the new hire can start with immediately. Include in onboarding program | -10 | 2026-08-02 | [Manager Name] | 2026-07-20 | On track |  |  | Manager
Preparation for start of new hire | Setup desk with IT | -2 | 2026-08-02 | [IT Contact Name] | 2026-07-30 | On track |  |  | IT
Preparation for start of new hire | Setup desk with stationary | -2 | 2026-08-02 | [Manager Name] | 2026-07-30 | On track |  |  | Manager
Preparation for start of new hire | Check-in with new hire and ask if pre-read package have been read, and answer any questions | -3 | 2026-08-02 | [Manager Name] | 2026-07-29 | On track |  |  | Manager
Preparation for start of new hire | Call new hire and make sure they know where to go for their first day | -1 | 2026-08-02 | [Manager Name] | 2026-07-31 | On track |  |  | Manager
Preparation for start of new hire | Create entire first months introduction program | -10 | 2026-08-02 | [Manager Name] | 2026-07-20 | On track |  |  | Manager
Preparation for start of new hire | Send introduction program to new hire and team | -10 | 2026-08-02 | [Manager Name] | 2026-07-20 | On track |  |  | Manager
Preparation for start of new hire | Prepare desk for first day | -1 | 2026-08-02 | [Manager Name] | 2026-07-31 | On track |  |  | Manager
Preparation for start of new hire | Schedule hand-over meeting with old manager, if relevant | 4 | 2026-06-20 | [Manager Name] | 2026-06-25 | Overdue |  |  | Manager
Preparation for start of new hire | Schedule team for lunch on first day | 4 | 2026-06-20 | [Manager Name] | 2026-06-25 | Overdue |  |  | Manager
Preparation for start of new hire | Plan for tour of relevant company buildings/areas and update onboarding program | 4 | 2026-06-20 | [Manager Name] | 2026-06-25 | Overdue |  |  | Manager
Preparation for start of new hire | Schedule introduction to meeting structure | 4 | 2026-06-20 | [Manager Name] | 2026-06-25 | Overdue |  |  | Manager
Preparation for start of new hire | Schedule introduction to financial management and current numbers | 4 | 2026-06-20 | [Manager Name] | 2026-06-25 | Overdue |  |  | Manager
Preparation for start of new hire | Schedule introduction with HR Partner and C&B specialist | 4 | 2026-06-20 | [Manager Name] | 2026-06-25 | Overdue |  |  | Manager
Preparation for start of new hire | Identify all current meetings that new hire should attend, and add to onboarding program | 0 | 2026-06-20 | [Manager Name] | 2026-06-20 | Overdue |  |  | Manager
Preparation for start of new hire | Update onboarding program with scheduled introductions | 4 | 2026-06-20 | [Manager Name] | 2026-06-25 | Overdue |  |  | Manager
Preparation for start of new hire | Schedule go and see with any relevant stakeholders. | 4 | 2026-06-20 | [Manager Name] | 2026-06-25 | Overdue |  |  | Manager
Preparation for start of new hire | Prepare handover templates on team | -11 | 2026-08-02 | [Manager Name] | 2026-07-17 | On track |  |  | Manager
Preparation for start of new hire | Prepare handover templates on tasks | -11 | 2026-08-02 | [Manager Name] | 2026-07-17 | On track |  |  | Manager
Preparation for start of new hire | Invite team to breakfast on first day | 0 | 2026-06-20 | [Manager Name] | 2026-06-20 | Overdue |  |  | Manager
Preparation for start of new hire | Schedule 1:1 meetings with manager. Weekly in trial period | 0 | 2026-06-20 | [Manager Name] | 2026-06-20 | Overdue |  |  | Manager
Introduction period |  |  |  |  | 2026-10-23 | On track
Introduction period | Welcome new hire at reception on the first day | 0 | 2026-08-02 | [Manager Name] | 2026-08-02 | On track |  |  | Manager
Introduction period | Pick-up computer, phone, cards, welcome package, etc. | 0 | 2026-08-02 | [Manager Name] | 2026-08-02 | On track |  |  | Manager
Introduction period | Show new hire to workspace | 0 | 2026-08-02 | [Manager Name] | 2026-08-02 | On track |  |  | Manager
Introduction period | Introduce new hire to everyone close to workspace | 0 | 2026-08-02 | [Manager Name] | 2026-08-02 | On track |  |  | Manager
Introduction period | Have breakfast with team | 0 | 2026-08-02 | [Manager Name] | 2026-08-02 | On track |  |  | Manager
Introduction period | Sit down with new hire and present first weeks onboarding program | 0 | 2026-08-02 | [Manager Name] | 2026-08-02 | On track |  |  | Manager
Introduction period | Setup computer | 0 | 2026-08-02 | [IT Contact Name] | 2026-08-02 | On track |  |  | IT
Introduction period | Show new hire contents of welcome package | 0 | 2026-08-02 | [Manager Name] | 2026-08-02 | On track |  |  | Manager
Introduction period | Show how printer works | 0 | 2026-08-02 | [Manager Name] | 2026-08-02 | On track |  |  | Manager
Introduction period | Test that the personnel card is working. | 0 | 2026-08-02 | [IT Contact Name] | 2026-08-02 | On track |  |  | IT
Introduction period | Instruct on how to call service desk and use onsite servicedesk | 0 | 2026-08-02 | [IT Contact Name] | 2026-08-02 | On track |  |  | IT
Introduction period | Instruct how to order stationary | 0 | 2026-08-02 | [Manager Name] | 2026-08-02 | On track |  |  | Manager
Introduction period | Explain parking rules and get permit | 0 | 2026-08-02 | [Manager Name] | 2026-08-02 | On track |  |  | Manager
Introduction period | Meet with buddy | 0 | 2026-08-02 | [Buddy Name] | 2026-08-02 | On track |  |  | Buddy
Introduction period | Tour of building | 0 | 2026-08-02 | [Manager Name] | 2026-08-02 | On track |  |  | Manager
Introduction period | Show restrooms, exits, evacuation plans | 0 | 2026-08-02 | [Manager Name] | 2026-08-02 | On track |  |  | Manager
Introduction period | Show kitchens and what you find there | 0 | 2026-08-02 | [Manager Name] | 2026-08-02 | On track |  |  | Manager
Introduction period | Instruct on how to get access to facilities outside normal working hours | 0 | 2026-08-02 | [Manager Name] | 2026-08-02 | On track |  |  | Manager
Introduction period | Lunch with new hire | 0 | 2026-08-02 | [Manager Name] | 2026-08-02 | On track |  |  | Manager
Introduction period | Setup phone | 0 | 2026-08-02 | [IT Contact Name] | 2026-08-02 | On track |  |  | IT
Introduction period | Setup and instruct in the use of Outlook and scheduling conference rooms | 0 | 2026-08-02 | [IT Contact Name] | 2026-08-02 | On track |  |  | IT
Introduction period | End day with a session to ask questions | 0 | 2026-08-02 | [Manager Name] | 2026-08-02 | On track |  |  | Manager
Introduction period | Explain how and where photos will be taken. | 0 | 2026-08-02 | [Manager Name] | 2026-08-02 | On track |  |  | Manager
Introduction period | Request that new hire put onboarding into calendar and verify that it happens | 0 | 2026-08-02 | [Manager Name] | 2026-08-02 | On track |  |  | Manager
Introduction period | Close day with Q&A session | 0 | 2026-08-02 | [Manager Name] | 2026-08-02 | On track |  |  | Manager
Introduction period | Walk through job description and key goals | 1 | 2026-08-02 | [Manager Name] | 2026-08-03 | On track |  |  | Manager
Introduction period | Walkthrough the Personnel handbook | 1 | 2026-08-02 | [Manager Name] | 2026-08-03 | On track |  |  | Manager
Introduction period | Review and Q&A based on pre-read package | 1 | 2026-08-02 | [Manager Name] | 2026-08-03 | On track |  |  | Manager
Introduction period | Introduction to intranet | 1 | 2026-08-02 | [Manager Name] | 2026-08-03 | On track |  |  | Manager
Introduction period | Review organization and where the new hire fits in | 1 | 2026-08-02 | [Manager Name] | 2026-08-03 | On track |  |  | Manager
Introduction period | Instruct in use of HR systems + get contacts setup with birthdates | 7 | 2026-08-02 | [Manager Name] | 2026-08-11 | On track |  |  | Manager
Introduction period | Instruct in financials | 7 | 2026-08-02 | [Manager Name] | 2026-08-11 | On track |  |  | Manager
Introduction period | Introduce new hire to meeting structure | 7 | 2026-08-02 | [Manager Name] | 2026-08-11 | On track |  |  | Manager
Introduction period | Introduction to HR contact persons | 7 | 2026-08-02 | [Manager Name] | 2026-08-11 | On track |  |  | Manager
Introduction period | 30-day check-in and feedback with new hire | 30 | 2026-08-02 | [Manager Name] | 2026-09-11 | On track |  |  | Manager
Introduction period | Schedule 2½ months evaluation | 7 | 2026-08-02 | [Manager Name] | 2026-08-11 | On track |  |  | Manager
Introduction period | Set bonus target and sign agreement | 30 | 2026-08-02 | [Manager Name] | 2026-09-11 | On track |  |  | Manager
Introduction period | Confirm first paycheck processed correctly | 35 | 2026-08-02 | [HR Contact Name] | 2026-09-18 | On track |  |  | HR
Introduction period | Setup pension with company pension provider | 60 | 2026-08-02 | [HR Contact Name] | 2026-10-23 | On track |  |  | HR
Introduction period | Enroll in health/life insurance benefits | 60 | 2026-08-02 | [HR Contact Name] | 2026-10-23 | On track |  |  | HR
Finished onboarding |  |  |  |  | 2026-12-18 | On track
Finished onboarding | Prepare trial period evaluation | 70 | 2026-08-02 | [Manager Name] | 2026-11-06 | On track |  |  | Manager
Finished onboarding | Complete trial period evaluation | 80 | 2026-08-02 | [Manager Name] | 2026-11-20 | On track |  |  | Manager
Finished onboarding | Inform HR about trial period evaluation outcome | 80 | 2026-08-02 | [Manager Name] | 2026-11-20 | On track |  |  | Manager
Finished onboarding | Review onboarding program with new hire and adapt for next time | 90 | 2026-08-02 | [Manager Name] | 2026-12-04 | On track |  |  | Manager
Finished onboarding | Set goals for the rest of the HR period wheel until next development talk | 100 | 2026-08-02 | [Manager Name] | 2026-12-18 | On track |  |  | Manager
StruktureretSundFornuft.dk
Formulas:
Deadline = MAX([Deadline, row below]:F9)
Deadline = WORKDAY([Offsetting date],[DaysOffset])
Status (automatic) = IF([Completed]="Yes","Completed",IF(TODAY()>[Deadline],"Overdue","On track"))

## Pre-read package
Preparation of pre-read package
| Folder | Item | Description | Who knows more? | Responsible for delivering material | Completed
| [Company] Introduction | - | Introductory material related to [Company], our value chain, our organizations, our strategy, our policies and more. |  |  | No
|  | [Company] Annual Reports | Copy of annual financial statements for [Company] A/S |  |  | No
|  | Policies and guidelines | All relevant policies and guidelines that are relevant for you. This is a mandatory read. |  |  | No
| [Company] Organization | - | Introductory material related to the general organization. This includes organizational charts, recordings from all-hands meetings and much more |  |  | No
|  | [Main Office] local overview | Maps of buildings, etc. |  |  | No
|  | Org chart | Org chart for organization |  |  | No
| Generic Skill Material | - | Material related to different generic skillsets, that I think is relevant in your position. |  |  | No
| HR Activity Calendar | - | Introduction to our HR calendar as well as some of the activities on the calendar. |  |  | No
|  | Bonus (comp) | The generic model we use for our bonus agreements. |  |  | No
|  | HR Activity calendar | The HR Activity Calendar with all activities and deadlines. This shows the turning of the calendar within our company. Worth familiarizing yourself with. |  |  | No
| Management Teams | - | Contains relevant information from the specific management teams that you will be part of. |  |  | No
StruktureretSundFornuft.dk

## Onboarding program
Date | Start | Duration | End | Activity | Where | Who | Purpose | DayOffset
2026-08-02 | 9:00 | 1 hour | 10:00 | Welcome & office tour | Office | Manager | Warm welcome and orientation | 0
2026-08-02 | 10:00 | 1 hour | 11:00 | IT equipment setup | IT area | IT | Get computer, phone, and accounts working | 0
2026-08-02 | 12:00 | 1 hour | 13:00 | Team lunch | Canteen | Team | Informal introduction to the team | 0
2026-08-02 | 14:00 | 1 hour | 15:00 | Meet your buddy | Office | Buddy | Introduction to onboarding buddy | 0
2026-08-02 | 15:30 | 30 minutes | 16:00 | Day 1 wrap-up Q&A | Office | Manager | Answer first-day questions | 0
2026-08-03 | 9:00 | 1 hour | 10:00 | Company & department overview | Meeting room | Manager | Understand company structure and strategy | 1
2026-08-03 | 10:00 | 1 hour | 11:00 | Job description & key goals review | Meeting room | Manager | Walk through job description and key goals | 1
2026-08-03 | 11:00 | 1 hour | 12:00 | HR paperwork & policies review | Meeting room | HR | Complete mandatory paperwork and policy sign-off | 1
2026-08-03 | 14:00 | 1 hour | 15:00 | Systems & tools training | Meeting room | IT | Learn core systems and tools | 1
2026-08-03 | 15:00 | 30 minutes | 15:30 | Pre-read package Q&A | Meeting room | Manager | Review and Q&A based on pre-read package | 1
2026-08-04 | 9:00 | 2 hours | 11:00 | Role-specific training | Meeting room | Manager | Introduction to core job responsibilities | 2
2026-08-04 | 13:00 | 1 hour | 14:00 | Meet key stakeholders | Office | Manager | Introduce to cross-functional contacts | 2
2026-08-05 | 9:00 | 2 hours | 11:00 | Shadow buddy | Office | Buddy | Learn day-to-day workflows | 3
2026-08-06 | 9:00 | 1 hour | 10:00 | First week check-in with manager | Meeting room | Manager | Review first week, answer questions | 4
2026-08-09 | 9:00 | 30 minutes | 9:30 | Team meeting | Meeting room | Team | Join regular team meeting | 7
2026-08-09 | 10:00 | 30 minutes | 10:30 | Introduction to HR Business Partner | Meeting room | HR | Meet HR Business Partner | 7
2026-08-09 | 10:30 | 30 minutes | 11:00 | Introduction to Compensation & Benefits | Meeting room | HR | Meet Compensation & Benefits contact | 7
2026-08-09 | 11:00 | 1 hour | 12:00 | Financials & HR systems walkthrough | Meeting room | IT | Instruct in financials and HR system | 7
2026-08-12 | 9:00 | 1 hour | 10:00 | Department deep-dive | Meeting room | Manager | Deeper understanding of department goals | 10
2026-08-16 | 9:00 | 30 minutes | 9:30 | 2-week 1:1 with manager | Meeting room | Manager | Check progress and gather feedback | 14
2026-08-23 | 9:00 | 30 minutes | 9:30 | First project assignment review | Meeting room | Manager | Assign and discuss first project/task | 21
2026-09-01 | 9:00 | 30 minutes | 9:30 | 30-day check-in | Meeting room | Manager | First-month feedback and check-in | 30
2026-09-01 | 10:00 | 30 minutes | 10:30 | TownHall presentation | TownHall meeting | Manager | Present new hire at TownHall | 30
StruktureretSundFornuft.dk
Formulas:
Date = StartDAte+[DayOffset]

## Welcome Email
Welcome Email Template
Emne: Hjertelig velkommen til [Company]
Kære [New Hire Name],
Hjertelig velkommen til [Company], [Team]. Jeg er rigtig glad for at vi har fået dig med på holdet, og jeg glæder mig til vores kommende samarbejde. Allerede her inden din første dag skal du lige vide 11 ting:
1) Min vigtigste prioritet er at du kan lide dit arbejde og at du er god til det. Hvis der er noget jeg kan gøre for at give dig mere arbejdsglæde og gøre dig mere effektiv, så sig til med det samme! Det er ikke idealisme, det er sund fornuft: en glad medarbejder er en produktiv medarbejder.
2) Jeg har ikke tænkt mig at belemre dig med endeløse lister af regler og procedurer. Du er et voksent menneske, og jeg stoler på at du kan bruge din sunde dømmekraft.
3) Du har min fulde tilladelse til at jokke i spinaten og lave fejl, når bare du altid sørger for at indrømme dine fejl, sige undskyld til dem det går ud over, og lære af fejlen. Husk: De eneste som aldrig laver fejl, er dem som aldrig laver noget... og jeg forventer at du laver meget.
4) Husk også at sige til mig når jeg laver bøf. Jeg laver masser af fejl, og jeg vil gerne høre om det så hurtigt som muligt, så kan jeg blive dygtigere.
5) Sørg for altid at være på jagt efter kollegaer, der gør deres job godt og gør en ekstra forskel, så du kan rose dem for deres gode arbejde. Jeg gør det selv så meget jeg kan, men jeg kan ikke gøre det alene, og har brug for din hjælp.
6) Hvis jeg en sjælden gang i mellem gør noget rigtig smart eller godt, så vil jeg da også gerne høre fra dig.
7) Jeg har altid tid til dig. Min kalender er tit fyldt, men den er aldrig så fuld at jeg ikke har tid til at du kan komme og stille spørgsmål eller bare få et godt råd - også når jeg er på barsel.
8) Jeg vil gerne lære dig at kende både som medarbejder og som menneske. Fortæl mig endelig om dit liv og din familie. Jeg vil især gerne høre, om de ting du går op i og hvad du brænder for her i livet.
9) Jeg er mere end din chef, jeg er også et menneske. Hvis der er noget jeg som menneske kan gøre for dig der ligger ud over dit arbejde, så sig til. Måske du er interesseret i at finde en kontakt inden for en given branche som jeg kender, måske du efter et par år har lyst til at prøve nye udfordringer i eller uden for [Company]. Under alle omstændigheder, så sig til. Dit liv og din arbejdsglæde er vigtig for mig.
10) Jeg forventer, at du tager ansvaret for din egen arbejdsglæde. Hvis du kan gøre noget i dag for at give dig selv, en kollega eller mig lidt mere arbejdsglæde, så gør det endelig!
11) Du må aldrig få så travlt at du glemmer at leve. Vi har tit travlt, men jeg tror på at det er vigtigt også at have tid til kæresten, en tur til træning og hvad der ellers betyder noget for dig. Husk på at du ikke kun skal have glæde på arbejde, men du skal også holde så meget fri at du kan have glæde i resten af dit liv.
Jeg håber at din tid hos [Company] vil bringe dig megen arbejdsglæde.
Mange hilsner
[Manager Name]
StruktureretSundFornuft.dk
Welcome Email Template (English)
Subject: Warm welcome to [Company]
Dear [New Hire Name],
A warm welcome to [Company], [Team]. I'm truly glad we got you on the team, and I'm looking forward to working together. Even before your first day, here are 11 things you should know:
1) My top priority is that you enjoy your work and that you're good at it. If there's anything I can do to give you more job satisfaction and make you more effective, tell me right away! This isn't idealism, it's common sense: a happy employee is a productive employee.
2) I don't intend to burden you with endless lists of rules and procedures. You're an adult, and I trust you to use your good judgement.
3) You have my full permission to mess up and make mistakes, as long as you always own up to them, apologize to anyone affected, and learn from them. Remember: the only people who never make mistakes are the ones who never do anything... and I expect you to do a lot.
4) Remember to tell me when I mess up too. I make plenty of mistakes myself, and I want to hear about them as soon as possible so I can get better.
5) Always keep an eye out for colleagues who do their job well and go the extra mile, so you can praise them for their good work. I do this myself as much as I can, but I can't do it alone - I need your help.
6) If I occasionally do something really smart or good, I'd love to hear that from you too.
7) I always have time for you. My calendar is often full, but never so full that I don't have time for you to come with questions or just get some good advice - even while I'm on leave.
8) I want to get to know you both as an employee and as a person. Please tell me about your life and your family. I'm especially keen to hear what matters to you and what you're passionate about in life.
9) I'm more than just your boss - I'm also a person. If there's anything I can do for you as a person, beyond work, let me know. Maybe you're interested in a contact within a particular industry that I know, or maybe after a couple of years you'd like to try new challenges inside or outside [Company]. Either way, just say so. Your life and your job satisfaction matter to me.
10) I expect you to take responsibility for your own job satisfaction. If there's something you can do today to give yourself, a colleague, or me a bit more job satisfaction, then go ahead and do it!
11) Never get so busy that you forget to live. We're often busy, but I believe it's important to also have time for your partner, a trip to the gym, and whatever else matters to you. Remember that you shouldn't only find enjoyment at work - you should also take enough time off to enjoy the rest of your life.
I hope your time at [Company] brings you a great deal of job satisfaction.
Best regards
[Manager Name]